## Meeting Cadence
GOVERNANCE MEETING CADENCE
WEEKLY OPERATIONAL REVIEWS (30 minutes)
Purpose: | Review leading indicators, flag blockers, make tactical decisions
Attendees: | Department Heads + relevant team leads
When: | Every Monday, 9:00-9:30 AM |  |  |  | Standing meeting, no cancellations
Format: | Stand-up style, fast-paced |  |  |  | No deep dives, escalate if needed
Weekly Agenda Template:
1. Leading Indicators Review (10 min) |  | Each department head reports 2-3 key metrics |  |  | Green/Yellow/Red status
2. Blockers & Issues (10 min) |  | What's preventing progress? |  |  | Action items assigned
3. Week Ahead Priorities (5 min) |  | What's critical this week? |  |  | Alignment check
4. Quick Wins (5 min) |  | Celebrate progress |  |  | Build momentum
MONTHLY STRATEGIC REVIEWS (90 minutes)
Purpose: | Review pillar progress, adjust resources, make strategic decisions
Attendees: | C-Suite + Pillar Owners + Finance
When: | First Wednesday of each month, 2:00-3:30 PM |  |  |  | Schedule 3 months ahead
Preparation: | Pillar owners submit updates 48 hours before |  |  |  | Template provided
Monthly Agenda Template:
1. Pillar Progress Review (45 min) |  | Each pillar owner presents: KPIs, milestones, budget burn, risks |  |  | Go/No-Go decisions
2. Resource Reallocation (20 min) |  | Requests to shift budget/people between pillars |  |  | Approve/Defer/Decline
3. Strategic Issues (20 min) |  | Items escalated from weekly reviews |  |  | Decisions or escalation
4. Next Month Priorities (5 min) |  | Confirm focus for coming month |  |  | Alignment
QUARTERLY BOARD REVIEWS (Full Day)
Purpose: | Report strategic progress, validate direction, secure board approval for changes
Attendees: | Board + C-Suite + Key Leaders
When: | Last week of each quarter |  |  |  | Q1: March, Q2: June, Q3: Sept, Q4: Dec
Preparation: | Board package due 1 week before meeting |  |  |  | Finance + Strategy leads
Quarterly Agenda Template:
1. Financial Performance (60 min) |  | Revenue, margins, cash flow vs targets |  |  | Approval of adjustments
2. Strategic Pillar Review (90 min) |  | Each pillar: progress, ROI, pivots needed |  |  | Continue/Adjust/Stop
3. Market & Competitive Update (30 min) |  | External factors affecting strategy |  |  | Strategic implications
4. Strategy Refresh Discussion (60 min) |  | Should we adjust vision/pillars/KPIs? |  |  | Approve changes
5. Next Quarter Preview (30 min) |  | Key initiatives and expected outcomes |  |  | Resource approval
ANNUAL STRATEGY REFRESH (2-3 days offsite)
• Purpose: Comprehensive strategy review and planning for next year
• Attendees: C-Suite + Key Leaders
• When: Q4 (typically November)
• Outcome: Updated Strategic Foundation Framework for board approval
COMMUNICATION RHYTHM
After This Meeting | Who Communicates | To Whom | Format | Timing | Key Message | Purpose
Weekly Operational | Department Heads | Their Teams | Email/Slack | Same day | Wins, challenges, priorities | Keep teams aligned
Monthly Strategic | CEO | All Employees | Town Hall/Email | Within 2 days | Progress, adjustments, focus | Transparency
Quarterly Board | CFO | All Employees | Video/Email | Within 1 week | Results, strategy health, next quarter | Build confidence
Annual Strategy | CEO | All Employees | All-Hands Meeting | Within 2 weeks | Year ahead vision and priorities | Align organization