## Governance Structure
AI GOVERNANCE STRUCTURE
LAYER 1: STEERING COMMITTEE
Members: | CEO, CFO, COO, CTO, Pillar Owners
Meeting Cadence: | Monthly, 90 minutes
Decision Rights: | Approve AI >$100K, allocate budget, resolve conflicts, go/no-go decisions
LAYER 2: PMO
Members: | PMO Lead, Technical Rep, Business Rep, Executive Sponsor
Meeting Cadence: | Weekly, 30 minutes
Decision Rights: | Approve <$25K, resolve blockers, escalate issues, coordinate dependencies
LAYER 3: DEPARTMENT OWNERS
Who: | Department heads, pillar owners, functional leaders
Meeting Cadence: | Weekly execution + weekly reporting to PMO
LAYER 4: WORKING GROUPS
Who: | Cross-functional teams (5-8 people), data scientists, engineers, analysts
Meeting Cadence: | Daily standups (15 min), weekly sprint planning

## Meeting Agendas
GOVERNANCE MEETING AGENDAS
WEEKLY PMO MEETING (30 minutes)
Minutes 0-15 | Initiative Updates | Each AI initiative reports progress, plans, blockers
Minutes 15-25 | Blocker Resolution | PMO resolves issues or escalates to steering
Minutes 25-30 | Dashboard & Actions | Review metrics, assign actions
MONTHLY STEERING COMMITTEE (90 minutes)
Minutes 0-20 | Portfolio Review | AI initiative health, KPIs, budget status
Minutes 20-60 | Strategic Decisions | Continue/pivot/kill, budget allocation, priorities
Minutes 60-80 | Risk & Issues | Major risks, escalated blockers, mitigation plans
Minutes 80-90 | Next Period | Preview upcoming decisions, action items

## Metrics Dashboard
AI GOVERNANCE METRICS DASHBOARD
STRATEGIC METRICS
Metric | Target | Current | Status | Trend | Owner
Pillar Progress | [Target] | [Current] |  |  | [Owner]
AI Initiative ROI | [Target %] | [Current %] |  |  | [Owner]
Risk Score | Low | [Current] |  |  | [Owner]
OPERATIONAL METRICS
Metric | Target | Current | Status | Trend | Owner
Initiative Health | Green | [Status] |  |  | [Owner]
Blocker Resolution Time | <1 week | [Current] |  |  | [Owner]
Budget Variance | <10% | [Current %] |  |  | [Owner]
ADOPTION METRICS
Metric | Target | Current | Status | Trend | Owner
User Adoption Rate | [Target %] | [Current %] |  |  | [Owner]
Productivity Impact | [Target] | [Current] |  |  | [Owner]
Employee Retention | [Target %] | [Current %] |  |  | [Owner]